## Sheet1
Sr. # | REPORT DATE | SITEID | Region | Office | SNAGS | MAIN_CATEGORY | SUB CATEGORY | STATUS | Closure Date | Snag Reported By | Domain | Remarks
1 | 2017-05-09 | SH0084 | Southern Oman | Duqqam | Rectifier cabinet door lock is broken | DELTA CABINET | DOOR LOCK | Open |  | QMS | Oo Support | Dependency
2 | 2017-05-09 | WU6711 | Southern Oman | Duqqam | cable tray and tower base concrete is cracked | CIVIL_WORK | Tower | Open |  | QMS | Oo Support | Major-CIVIL
3 | 2017-05-10 | SH0061 | Southern Oman | Duqqam | Fiber cables not arranged properly | CABLE DRESSING | CABLE DRESSING | Open |  | QMS | Oo Support | Dependency
4 | 2017-05-10 | WU0760 | Southern Oman | Duqqam | Lighting rod cable is missing | GROUNDING | GROUNDING | Open |  | QMS | Oo Support | Major-GROUNDING
5 | 2017-05-23 | BA0110 | Northern Oman | Sohar | shelter 2 step ladder concrete is broken | CIVIL_WORK | Indoor Shelter | Open |  | QMS | Oo Support | Major-CIVIL
6 | 2017-05-22 | BA0198 | Northern Oman | Suwaiq | main gate i getting rusty and concrete support s are cracked | CIVIL_WORK | Fence / Boundry Wall / Main Gate | Open |  | QMS | Oo Support | Major-CIVIL
7 | 2017-06-08 | MU0748 | Northern Oman | Muscat | extra antenna inside site area | EXTRA MATERIAL | EXTRA MATERIAL | Open |  | QMS | Oo Support | Omantel Support
8 | 2017-06-14 | MU0114 | Northern Oman | Muscat | Boundary wall is damaged | CIVIL_WORK | Fence / Boundry Wall / Main Gate | Open |  | QMS | Oo Support | Major-CIVIL
9 | 2017-06-20 | BA0089 | Northern Oman | Sohar | Tower grounding missing | GROUNDING | GROUNDING | Open |  | QMS | Oo Support | Major-GROUNDING